## Consolidated POA&M
ID | Category | Scenario / Weakness Description | Technical Root Cause | Business Impact | Action Plan | Regulatory Mapping | POC | Risk | Status | Target Completion Date
W-2026-001 | Endpoint Security | 22 laptops in the Finance Dept are 3 months behind on cumulative security updates; automated patching is failing due to disk space exhaustion. | C: drive storage full (95%) prevented the Windows Update agent from staging files; clean-up scripts were not part of the standard agent health check. | High risk of exploitation via local elevation of privilege; failure to meet Cyber Essentials compliance. | Run automated disk cleanup via Intune to clear WinSxS and Temp folders; force patch install during scheduled 8 PM maintenance window. | NIST SI-2 | Desktop Engineering | High | In Progress | 2026-05-10
W-2026-002 | Identity Management | Legacy ERP system allows 6-character passwords and does not lock out accounts after failed attempts. | Application-level authentication module is hardcoded and does not integrate with Azure AD/LDAP complexity policies. | Increased vulnerability to brute-force attacks on financial data records. | Deploy an LDAP proxy to intercept and enforce password complexity; migrate ERP auth to SAML/SSO by Q4. | NIST AC-2 | App Dev Lead | Medium | Open | 2026-09-01
W-2026-003 | Cloud Security | 30% of global O365 mailboxes still bypass MFA because they are marked as 'Legacy Service Accounts' but are used by human contractors. | Misclassification in the User Directory; lack of a Conditional Access policy for external partners. | Critical risk of Account Takeover (ATO) leading to Business Email Compromise (BEC). | Re-classify accounts; enforce MFA via Azure Conditional Access for all accounts with human login signatures. | PCI-DSS 8.3 | Cloud Admin | High | Open | 2026-06-15
W-2026-004 | Business Continuity | Production SQL database backups are stored on the same physical SAN as the live database. | Improper storage tiering configuration; lack of off-site/off-host replication. | Single point of failure; hardware failure or ransomware would result in total data loss. | Configure secondary backup stream to AWS S3 Glacier with Object Lock (Immutability); verify recovery time objective (RTO). | NIST CP-9 | Storage Eng. | High | Open | 2026-07-15
W-2026-005 | Physical Security | Primary server room door latch is worn, allowing it to be pulled open without a badge swipe. | Mechanical fatigue of the strike plate; failure of the annual facilities maintenance audit to catch hardware wear. | Unauthorized physical entry to the core network switches and compute infrastructure. | Replace mechanical strike plate with heavy-duty magnetic lock; install door-contact alarm to notify SOC if door is ajar. | NIST PE-3 | Facilities Mgr | Medium | In Progress | 2026-11-30 | 0
W-2026-006 | Supply Chain | CI/CD pipelines pull open-source JavaScript libraries from public NPM without verifying checksums or signatures. | Absence of a private artifact repository (like Artifactory) to proxy and scan external dependencies. | Vulnerability to 'Dependency Confusion' attacks where malicious code is injected into the build process. | Implement Nexus/Artifactory as a gated proxy; mandate SBOM generation for every production build. | NIST SR-4 | DevSecOps | Critical | Planned | 2026-06-15
W-2026-007 | Network Security | Smart TVs and IoT coffee machines in the breakroom are connected to the main 'Corp-Internal' Wi-Fi. | Lack of network segmentation; easy-to-guess PSK (Pre-Shared Key) used for guest and IoT devices. | Lateral movement; an attacker could use a compromised TV to sniff traffic on the corporate network. | Migrate all IoT devices to a dedicated VLAN with no cross-talk to production subnets; enforce MAC-address filtering. | ISO 27001 A.13 | Network Eng. | High | Not Started | 2026-07-15
W-2026-008 | API Security | The 'Partner-API' lacks rate-limiting, allowing 50,000 requests per minute from a single IP. | API Gateway configuration was left on 'Default' bypass mode during the last migration. | Denial of Service (DoS) risk and scraping of the entire product catalog by competitors. | Apply per-client rate-limiting at the Kong Gateway level; implement geographic blocking for non-operating regions. | OWASP API 4 | API Lead | Medium | In Progress | 2026-09-15
W-2026-009 | Data Privacy | Developer 'Sandbox' databases contain un-masked production customer data (PII). | Production-to-Dev refresh script does not include the data-masking module. | GDPR breach risk; non-production environments typically have lower security controls. | Automate data obfuscation (masking) during the ETL process from Production to Dev; delete existing unmasked dumps. | GDPR Art. 32 | DBA Team | High | Open | 2026-06-15
W-2026-010 | Privileged Access | Service accounts for the 'Backup-Agent' have Domain Admin rights but don't require them. | Over-privileged permissioning chosen during initial setup to avoid 'Access Denied' errors. | If the backup agent is compromised, the attacker has full domain control. | Implement Principle of Least Privilege (PoLP); restrict agent to specific backup operators group with limited file-read rights. | NIST AC-6 | Windows Admin | High | Planned | 2026-06-30
W-2026-011 | Incident Response | The Incident Response Plan (IRP) has not been updated to include procedures for Ransomware-as-a-Service (RaaS) scenarios. | Annual plan review was skipped due to staff turnover in the Security Office. | Delayed response and confusion during a real breach, leading to higher ransom costs and downtime. | Draft a Ransomware-specific playbook; conduct a cross-departmental tabletop exercise with Legal and PR. | NIST IR-4 | CISO | Medium | Open | 2026-09-30
W-2026-012 | Log Management | Firewall logs are only retained for 7 days due to SIEM storage constraints. | Storage volume for the ELK stack was not resized to accommodate new 10Gbps traffic logs. | Inability to perform forensic analysis on older breaches (typical dwell time is 200+ days). | Upgrade SIEM storage capacity; implement log-rotation and cold-storage archiving to S3 for 1-year retention. | PCI-DSS 10.7 | SOC Manager | High | Planned | 2026-07-15
W-2026-013 | Governance | Offboarding process for contractors does not include revoking physical badge access to the data center. | HR system and Badge Access system are not integrated (Manual process failure). | Ex-contractors retain physical access to secure facilities for months after contract end. | Integrate the Badge System (Lenel/S2) with Active Directory to auto-disable badges when accounts expire. | ISO 27001 A.8.1 | Physical Sec | Medium | Open | 2026-09-01
W-2026-014 | Vulnerability Mgmt | Internal HR portal is running an EOL (End-of-Life) version of Apache Struts. | Legacy application code is incompatible with newer Struts versions; requires a full rewrite. | Vulnerability to critical RCE (Remote Code Execution) exploits targeting the HR database. | Place the portal behind a WAF with virtual patching; schedule application modernization project for Q3. | NIST SI-2 | AppSec | Critical | In Progress | 2026-05-15
W-2026-015 | AI Governance | Employees are inputting proprietary source code into public GenAI tools for debugging. | Lack of an 'Acceptable Use' policy for AI and no technical blocking of AI domains. | Loss of Intellectual Property (IP); potential for the AI model to leak secret keys to other users. | Implement CASB (Cloud Access Security Broker) to monitor AI usage; provide internal, secure 'Private-GPT' instance. | NIST AI RMF | CISO / Legal | High | Open | 2026-08-15
W-2026-016 | Mobile Security | Unmanaged personal mobile devices (BYOD) can download sensitive email attachments locally. | Intune Mobile Application Management (MAM) policies are not enforced for 'Outlook for Mobile'. | Data leakage if a personal phone is lost or sold without being wiped. | Apply MAM policies to prevent 'Save-As' to local storage; mandate App-Protection-Policies for all BYOD users. | NIST AC-19 | Intune Admin | Medium | Planned | 2026-09-15
W-2026-017 | Threat Intel | No automated detection for company-specific credential leaks on the 'Dark Web'. | Absence of a Digital Risk Protection Service (DRPS) subscription. | Employees using leaked passwords across multiple systems can be compromised before the company is aware. | Procure a Threat Intel service (e.g., Recorded Future/Flashpoint) to alert on domain-specific credential drops. | NIST RA-5 | SOC Lead | Medium | Not Started | 2026-09-30
W-2026-018 | Operational Risk | Primary ISP and Secondary ISP share the same physical entry point into the building (Single conduit). | Facilities oversight during the initial building fit-out. | A single street-level construction event (backhoe) could cause a total internet outage. | Contract a third ISP via a different physical path (e.g., roof-top microwave or different street entrance). | NIST CP-4 | Network Ops | Medium | Planned | 2026-10-30
W-2026-019 | Container Security | Production Docker images are using 'latest' tags instead of specific immutable hashes. | Inconsistent developer practice; lack of 'image-pinning' requirements in the CI/CD pipeline. | Unpredictable production environments; potential to pull a compromised 'latest' image from a public repo. | Update CI/CD to enforce Digest/SHA pinning; scan images for vulnerabilities before every deployment. | NIST 800-190 | DevOps Eng. | High | In Progress | 2026-08-30
W-2026-020 | Encryption | Internal file-share server uses SMB v1.0 which is susceptible to man-in-the-middle attacks. | Legacy scanners require SMBv1 to send scans-to-folder. | Susceptibility to ransomware lateral movement (e.g., WannaCry) and credential sniffing. | Upgrade scanners or use SFTP for scan-to-folder; disable SMBv1 globally via Group Policy. | NIST SC-8 | Infra Team | Critical | Open | 2026-06-15
W-2026-021 | Disaster Recovery | Disaster Recovery site is located 5 miles from the Primary site, within the same 100-year flood zone. | Cost-saving measures during initial DR site selection. | A regional natural disaster (flood/hurricane) would disable both primary and backup operations. | Migrate DR warm-standby to a different geographic region (at least 100 miles away) or a different cloud region. | NIST CP-7 | BCP Lead | High | Planned | 2026-08-30
W-2026-022 | Third Party Risk | Critical payroll vendor has an expired SOC2 Type 2 report (expired 6 months ago). | Vendor Risk Management (VRM) software was not configured to send renewal alerts. | Loss of assurance regarding the vendor's internal controls over sensitive financial/employee data. | Issue a formal security request to the vendor; perform a manual risk assessment if the audit is delayed. | SOC2 / ISO 27001 | Risk Mgmt | Medium | Open | 2026-10-01
W-2026-023 | Asset Management | The CMDB (Asset Inventory) shows a 15% discrepancy between actual and recorded server counts. | Automated discovery tools are blocked by local firewalls on specific subnets. | Inability to apply patches or security controls to 'Ghost' assets that are not officially managed. | Adjust firewall rules to allow the 'ServiceNow' discovery agent; perform a manual rack audit to reconcile. | CIS Control 1 | Asset Mgr | High | In Progress | 2026-08-15
W-2026-024 | Web Security | Abandoned marketing micro-sites (e.g., 'summer-promo-2022.company.com') are still live and unpatched. | Lack of a 'Web-Decommissioning' process once a marketing campaign ends. | Subdomain takeover risk; these sites serve as easy entry points for attackers via old WordPress vulnerabilities. | Scan for all company-owned subdomains; decommission all sites not found on the 'Approved Web List'. | NIST SI-2 | Webmaster | Medium | Open | 2026-10-15
W-2026-025 | Identity (Zero Trust) | VPN users are granted access to the entire internal subnet rather than specific application ports. | Legacy VPN architecture (Client-to-Site) without micro-segmentation. | Large blast radius; a single compromised VPN account allows an attacker to scan the entire internal network. | Transition to a Zero-Trust Network Access (ZTNA) model; enforce app-specific tunnels using Per-App VPN. | NIST 800-207 | Network Sec | High | Planned | 2026-08-31

## Target Time Frame Matrix
Risk Level | Logic | Typical Target Date
Critical | Immediate danger; fix now. | May - June 2026
High | Serious exposure; fix soon. | June - August 2026
Medium | Important but not urgent. | September - October 2026
Long-Term | Major architecture/physical changes. | November - December 2026